## Slide 1: Maximizing Success on Integrated Projects: An Owner’s Guide
An Owner’s Only Presentation
September 9, 2016
Greg Gidez, DBIA, AIA
Keith Molenaar, PhD, DBIA

## Slide 2: Collaboration
What is COLLABORATION?
col·lab·o·rate
kəˈlabəˌrāt/
verb: collaborate;
work jointly on an activity, especially to produce or create something.

## Slide 3
What is Integration?
in·te·grate
ˈin(t)əˌɡrāt/
verb: integrate
combine (one thing) with another so that they become a whole.
bring (people or groups with particular characteristics or needs) into equal participation
Notes: Simplistically a project can be broken down into two phases, the solution phase (design) and the schedule (or construction assembly) phase. You can’t get to the schedule, if you can’t get to the solution. Designers are trained to solve problems and will continue to noodle on the solution until the fees run out. Your job is to make sure that they have the right info at the right time to make the right design decision and arrive at the solution. The solution phase includes the Owner. An AWOL Owner is not around to make decisions and guide the team. So managing the Owner is as important as managing the designers. You are managing the information to effectively develop the design.

## Slide 4
INTEGRATION IS A TEAM SPORT
POETRY IN MOTION
Notes: Simplistically a project can be broken down into two phases, the solution phase (design) and the schedule (or construction assembly) phase. You can’t get to the schedule, if you can’t get to the solution. Designers are trained to solve problems and will continue to noodle on the solution until the fees run out. Your job is to make sure that they have the right info at the right time to make the right design decision and arrive at the solution. The solution phase includes the Owner. An AWOL Owner is not around to make decisions and guide the team. So managing the Owner is as important as managing the designers. You are managing the information to effectively develop the design.

## Slide 5
co·he·sion
kōˈhēZHən/
noun: cohesion
the action or fact of forming a united whole.

## Slide 6
What is an integrated project?
Notes: Simplistically a project can be broken down into two phases, the solution phase (design) and the schedule (or construction assembly) phase. You can’t get to the schedule, if you can’t get to the solution. Designers are trained to solve problems and will continue to noodle on the solution until the fees run out. Your job is to make sure that they have the right info at the right time to make the right design decision and arrive at the solution. The solution phase includes the Owner. An AWOL Owner is not around to make decisions and guide the team. So managing the Owner is as important as managing the designers. You are managing the information to effectively develop the design.

## Slide 7
What is Project success?
Notes: Simplistically a project can be broken down into two phases, the solution phase (design) and the schedule (or construction assembly) phase. You can’t get to the schedule, if you can’t get to the solution. Designers are trained to solve problems and will continue to noodle on the solution until the fees run out. Your job is to make sure that they have the right info at the right time to make the right design decision and arrive at the solution. The solution phase includes the Owner. An AWOL Owner is not around to make decisions and guide the team. So managing the Owner is as important as managing the designers. You are managing the information to effectively develop the design.

## Slide 8
For the Owner?
For the Architect?
For the Engineer?
For the Builder?
For the Trade?
For the user?
Notes: Simplistically a project can be broken down into two phases, the solution phase (design) and the schedule (or construction assembly) phase. You can’t get to the schedule, if you can’t get to the solution. Designers are trained to solve problems and will continue to noodle on the solution until the fees run out. Your job is to make sure that they have the right info at the right time to make the right design decision and arrive at the solution. The solution phase includes the Owner. An AWOL Owner is not around to make decisions and guide the team. So managing the Owner is as important as managing the designers. You are managing the information to effectively develop the design.

## Slide 9: WHAT IS THE RESEARCH?
Notes: Greg
Key Point
This theory is not just HP, but it has been proved through research in the industry.

## Slide 10: Project Delivery Research
In 1997-1998 the Construction Industry Institute in collaboration with Penn State University published seminal research indicating Design Build out performed CM at Risk or Design Bid Build in terms of
  Lower cost,
  Improved schedule
  Better quality
Metric | DB vs. DBB | CM@R vs. DBB | DB vs. CM@R
Unit Cost | 6.1% lower | 1.6% lower | 4.5% lower
Construction Speed | 12% faster | 5.8% faster | 7% faster
Delivery Speed | 33.5% faster | 13.3% faster | 23.5% faster
Cost Growth | 5.2% less | 7.8% more | 12.6% less
Schedule Growth | 11.4% less | 9.2% less | 2.2% less
1998 CII RT 133 Research
The more integrated, the better the performance
Singular vs multiple contracts

## Slide 11: Team Integration and Sustainability
  When sustainability is a goal –
  The higher the level of team integration the higher the performance of the building
  The greater the Owner involvement, the better the opportunity to achieve sustainable goals
https://www.dbia.org/resource-center/Documents/
CPF_ThrustII_05212010_Final.pdf

## Slide 12: Impacts of the Previous Research
Many State and Federal agencies changed procurement laws to permit alternate forms of project delivery
Owner’s turned to Design Build and CMR to increase potential for project success
Demand for sustainability has driven demand for integrated approaches

## Slide 13: What has Changed?
Is the previous research still relevant?
What has changed?
  Technology
  Building Information Modeling
  IPD, Progressive DB, P3
  Construction technologies
  Economy
  Level of sophistication
What are the factors that improve outcomes in any project delivery strategy?

## Slide 14
How can an Owner best structure the project for a successful outcome?

## Slide 15: Maximizing Success in Integrated Projects: An Owner’s Guide
• Greg Gidez (co-chair), Hensel Phelps Construction Co.
• Mark Konchar (co-chair), Balfour Beatty Construction
• Howard W. Ashcraft, Esq., Hanson Bridgett LLP
• Spencer Brott, Trammell Crow Real Estate Services, Inc.
• Bill Dean, M.C. Dean, Inc.
• Tom Dyze, Walbridge
• Matthew Ellis, US Army Corps of Engineers
• Behzad Esmaeili, University of Nebraska-Lincoln
• Bryan Franz, University of Florida
Diana Hoag, Xcelsi Group, LLC
• Mike Kenig, Holder Construction
• Robert Leicht, Penn State University
• Russell Manning, Department of Defense
• John Messner, Penn State University
• John Miller, Barchan Foundation, Inc.
• Keith Molenaar, Univ. of Colorado
• Brendan Robinson, U.S. Architect of the Capitol
• Victor Sanvido, Southland Industries
• Ronald Smith, Kaiser Permanente
• David P. Thorman, Former California State Architect

## Slide 16
Team
Integration
Group Cohesion
Integration
Participation in:
    Joint Goal Setting
    Cross Disciplinary design charrettes
    BIM Execution Planning
Increased sharing of information and analysis through BIM
Increased team interaction through colocation
  Higher levels of integration led to:
Reduced schedule growth
Enabled more intense schedules
Led to more cohesive teams
Degree to which team members from separate organizations and disciplines are engaged in collaborative activities

## Slide 17
Team
Integration
Group Cohesion
Group Cohesion
Degree to which team, as individuals, have shared, task commitment, group pride, and interpersonal alignment
Commitment to shared goals
High levels of team chemistry
Communication is timely and effective
  Higher group cohesiveness led to:
Reduced cost growth
Higher system quality
Improved turnover experience

## Slide 18
Team Integration
Team Integration
Group Cohesion
Factor Value

## Slide 19
70%
of projects delivered late had below average levels of Team Integration
Team Integration
Group Cohesion
Factor Value

## Slide 20
60%
of on budget projects had above average levels of Group Cohesion
Team Integration
Group Cohesion
Factor Value

## Slide 21
DBB
Team Integration
Group Cohesion
Delivery Method

## Slide 22
CM@R
Team Integration
Group Cohesion
Delivery Method

## Slide 23
DB
Team Integration
Group Cohesion
Delivery Method

## Slide 24
IPD
Team Integration
Group Cohesion
Delivery Method

## Slide 25
Delivery Method
DBB
CM@R
DB
IPD
Large variance within each delivery method
We need to consider more than just delivery method
Team Integration
Group Cohesion

## Slide 26
How did we come to these findings?

## Slide 27
Research Charrette
A structured 2-day workshop that combined surveys and focus group discussion
Attendees: CM/GCs, specialty contractors, owners, lawyers, architects
Study Background

## Slide 28
The Role of Team Integration in Project Performance
Methodology: Empirical Study
Large-sample data collection
Latent variable analysis
Structural modeling of relationships
Sponsors:
Charles Pankow Foundation
Construction Industry Institute (CII)
Study Background

## Slide 29
Data Set
Completed: 2008 - 2013
Public: 127 (62%)
Private: 77 (38%)
204 Projects
56 (27%)
Educational
41 (20%)
Office
32 (16%)
Health Care
27 (13%)
Lodging
20 (10%)
Commercial
11 (5%)
Sports & Recreation
11 (5%)
Manufacturing
4 (2%)
Correctional
2 (1%)
Transportation
Facility Types
Number of Projects
1
32
Facility Sizes
(44%) 90
0 - 99,000 ft2
(24%) 49
100,000 - 199,000 ft2
(13%) 26
200,000 - 299,000 ft2
(7%) 15
300,000 - 399,000 ft2
(3%) 6
400,000 - 499,000 ft2
(2%) 3
500,000 - 599,000 ft2
(3%) 7
> 700,000 ft2
600,000 - 699,000 ft2
(4%) 8

## Slide 30
The Factors
Group Cohesion
Development into an
effective unit
Team Integration
Bringing together In
high-quality interactions
Cost
Quality
Project Performance
Schedule
Delivery Strategy
Plan for structuring design
and construction services

## Slide 31
Offsite Prefabrication
Measurements of participation in high-quality interactions, suspected to be driven by the level of team integration:
BIM planning
Design charrettes
Proportion of core* project team participating in:
Number of BIM uses from a predefined list
Co-location
Percentage of offsite prefabrication
*Includes owner, designer, primary contractor, MEP trades and structural trades
.72
.43
.61
.50
.57
Number of BIM Uses
BIM Planning Participation
Charrette Participation
Co-location Participation
R2=.51
R2=.34
R2=.25
R2=.18
Goal Setting Participation
R2=.32
Goal setting
The Factors
Team Integration
Bringing together In
high-quality interactions

## Slide 32
Group Cohesion
Development into an
effective unit
Team Integration
Bringing together In
high-quality interactions
Cost
Quality
Project Performance
Schedule
Delivery Strategy
Plan for structuring design
and construction services
The Factors

## Slide 33
Formality of Communication
Frequency of Compromise
Team
Chemistry
Timeliness of Communication
Goal
Commitment
R2=.64
R2=.58
R2=.68
.80
.76
.83
Excellent
Poor
Measures of the team environment, thought to be reflective of the level of group cohesion:
Timeliness of communication
Commitment to project goals
Team chemistry
Frequency of compromise
Formality of communication
Strongly
Weakly
Always on time
Never on time
Group Cohesion
Development into an
effective unit
The Factors

## Slide 34
Group Cohesion
Development into an
effective unit
Team Integration
Bringing together In
high-quality interactions
Cost
Quality
Project Performance
Schedule
Delivery Strategy
Plan for structuring design
and construction services
The Factors

## Slide 35
Measurements of the project organization that reflect the owner’s delivery strategy
Single contract for design and construction
Builder was hired at
SD or earlier
Trades were hired at
SD or earlier
Builder was
prequalified
Trades were
prequalified
Builder was selected
based on cost of work
Trades were selected
based on cost of work
Builder had an open
book contract
Delivery Strategy
Plan for structuring design
and construction services
Delivery Method
Payment Terms
Procurement Process
Class I
Class II
Class III
Class IV
Class V
The Factors

## Slide 36
Percentage of Projects
Phase of Design
Class I (n=19)
Class III (n=54)
Class V (n=36)
PRE = Pre-Design
CONC = Conceptual Design
SD = Schematic Design
DD = Design Development
CD = Construction Documents
BID = Bidding
Timing of Involvement
Primary Contractor / CM
Trade Contractors
Early Involvement of the Builder and/or Trades
Class I
Class II
Class III
Class IV
Class V
Project Delivery Strategy

## Slide 37
Early Involvement of the Builder and Trades
Underlying Themes
Class I
Class II
Class III
Class IV
Class V
Project Delivery Strategy
Open Book Payment Terms
Qualification Based Selection

## Slide 38
I
II
III
IV
V
Delivery Strategy
Team Integration
Group Cohesion

## Slide 39: The Owner’s Guide Pulling it all together
Reduced schedule growth
Enabled more intense schedules
Led to more group cohesion
Reduced cost growth
Improved turnover experience
Higher system quality

## Slide 40: How do I use this information for my projects?

## Slide 42
Workshop
Workshop Goal
Identify the targeted delivery
strategy for your project
Bring together key stakeholders BEFORE setting the strategy
Preparation:
Outline of project scope and goals
Define / invite key stakeholders
Approximate timeline / budget

## Slide 43: The Process
1. Define Project Needs
Assess goals for management and performance
Document project summary information (e.g. size, type, etc.)
Determine project goals (e.g. time, cost, quality, etc.)
2. Explore Delivery Options
Discuss delivery decisions with attention to integrated processes and team cohesion
1a.
1b.
2a-b.
2c.
2d-g.
Discuss organizational structure (single vs. split D&C contracts, timing of core team involvement)
Discuss contract payment terms for builder and key trades (open vs. closed book)
Discuss team assembly (e.g. selection process and criteria, prior experience, etc.)
Owner’s Project Delivery Strategy
– Project summary
– Project goals
– Etc.
3. Select Delivery Strategy
Identify an optimal delivery strategy consistent with owner constraints
3a.
3b.
Identify owner’s legal and policy constraints (e.g. procurement law, staff experience, etc.)
Determine strategy by comparing to research results (e.g. Classes I-V)
3c.
Select and Implement Project Delivery Strategy

## Slide 44
Define Project Needs
Document project summary information
Determine project goals
Formally document the project purpose and scope
a.
b.
Step 1a

## Slide 45
Define Project Goals
Define the specific goals for the project and functionality of the completed facility.
Schedule
Accelerate start of project revenue
Cost
Maximize value for project budget
Complete the project on budget
Functional
Minimize inconvenience to current facility users
Document project summary information
Determine project goals
a.
b.
Step 1b

## Slide 46
Explore Delivery Options
Org.
Structure
Payment Terms
Discuss the organizational structure
a-b.
c.
Team Assembly Process
d-g.
Design Responsibility
  Shared contract or split
Early Involvement
  Builder
  Specialty Trades
Timing of Involvement
Pre-Schematic Design
Late Design
Post-Design
Step 2a-b

## Slide 47
Builder Payment Terms
Discuss the contract payment terms
Open Book
Cost-reimbursable
Guaranteed Max Price or Cost Plus
Closed Book
Schedule of Values
  Lump Sum Price
Specialty Contractor Payment Terms
Step 2c
Org.
Structure
Payment Terms
a-b.
c.
Team Assembly Process
d-g.

## Slide 48
Explore Team Assembly
Discuss the team assembly process
Selection Criteria
Bid price
Best Value
Qualification Based Selection
Prequalification
Prequalify
Open Procurement
Specialty Trade Procurement
Selection Criteria
Prequalification
Step 2d-g
Org.
Structure
Payment Terms
a-b.
c.
Team Assembly Process
d-g.

## Slide 49
Identify Constraints
Identify Constraints
Discuss legal or policy constraints
a.
b.
Reflect on consistency of strategy
c.
Compare delivery decisions
Step 3a

## Slide 50
Compare by Strategy
Apply underlying themes to inform strategy decisions
Step 3b
Identify Constraints
a.
b.
Reflect on consistency of strategy
c.
Compare delivery decisions

## Slide 51
Reflect on Consistency
Regardless of the selected strategy, consider implementing these critical success factors:
BIM planning
Design charrettes
Proportion of core* project team participating:
Number of BIM uses from a predefined list
Co-location
Goal setting
Timeliness of communication
Commitment to project goals
Team chemistry
Behaviors leading to Team Cohesion
Integrated Processes
Step 3c
Identify Constraints
a.
b.
Reflect on consistency of strategy
c.
Compare delivery decisions

## Slide 52
http://bim.psu.edu/delivery

## Slide 53: How can you help inform the process?

## Slide 54
GET SMART
1st THING
Notes: Simplistically a project can be broken down into two phases, the solution phase (design) and the schedule (or construction assembly) phase. You can’t get to the schedule, if you can’t get to the solution. Designers are trained to solve problems and will continue to noodle on the solution until the fees run out. Your job is to make sure that they have the right info at the right time to make the right design decision and arrive at the solution. The solution phase includes the Owner. An AWOL Owner is not around to make decisions and guide the team. So managing the Owner is as important as managing the designers. You are managing the information to effectively develop the design.

## Slide 55
MAKE THE MENTAL SHIFT
Notes: Simplistically a project can be broken down into two phases, the solution phase (design) and the schedule (or construction assembly) phase. You can’t get to the schedule, if you can’t get to the solution. Designers are trained to solve problems and will continue to noodle on the solution until the fees run out. Your job is to make sure that they have the right info at the right time to make the right design decision and arrive at the solution. The solution phase includes the Owner. An AWOL Owner is not around to make decisions and guide the team. So managing the Owner is as important as managing the designers. You are managing the information to effectively develop the design.

## Slide 56
RIGHT PERSON IN THE RIGHT SEAT ON THE BUS
Notes: Simplistically a project can be broken down into two phases, the solution phase (design) and the schedule (or construction assembly) phase. You can’t get to the schedule, if you can’t get to the solution. Designers are trained to solve problems and will continue to noodle on the solution until the fees run out. Your job is to make sure that they have the right info at the right time to make the right design decision and arrive at the solution. The solution phase includes the Owner. An AWOL Owner is not around to make decisions and guide the team. So managing the Owner is as important as managing the designers. You are managing the information to effectively develop the design.

## Slide 57
INTEGRATION IS A TEAM SPORT
POETRY IN MOTION
Notes: Simplistically a project can be broken down into two phases, the solution phase (design) and the schedule (or construction assembly) phase. You can’t get to the schedule, if you can’t get to the solution. Designers are trained to solve problems and will continue to noodle on the solution until the fees run out. Your job is to make sure that they have the right info at the right time to make the right design decision and arrive at the solution. The solution phase includes the Owner. An AWOL Owner is not around to make decisions and guide the team. So managing the Owner is as important as managing the designers. You are managing the information to effectively develop the design.

## Slide 58
Procurement
Contracts
Execution
Notes: Greg
Design Phase Management is a soup to nuts proposition. It begins before the project is awarded and is managed throughout. Consider a project where HP Services might be involved. Knowing how the building will be operated influences the design, and that should be discussed at the design commencement.
So effective design management starts in the procurement phase and continues throughout the life cycle of the project. Knowing when we are contractually obligated to support the design phase is important, as well as knowing the risk profiles of different delivery strategies will inform on how best to manage the work
58

## Slide 59
OWNERS

## Slide 60: Impacts of this Research
Federal Owners and State agencies are strategically determining best project delivery strategies to maximize success
Maximizing success requires a holistic strategy, an integrated team and a motivated group of individuals

## Slide 61: What you should remember?
Best path to project success is through building a TEAM – integration / cohesion
Teams are influenced through project delivery decisions – early involvement, open book, qualifications driven
Project Delivery needs to be developed as a strategy across the project

## Slide 62: Maximizing Success on Integrated Projects: An Owner’s Guide
An Owner’s Only Presentation
September 9, 2016
Greg Gidez, DBIA, AIA
Keith Molenaar, PhD, DBIA