## Slide 1: DBIA Webinar #6
Design-Build Acquisition and Contract Incentives July 19, 2018
Presented by Evan Caplicki, Esq.

## Slide 2: Outline
DBIA Best Practices
Design-Build Procurements
Design-Build Contracts
  Completion Milestones
  Other

## Slide 3: DBIA Best Practices
Design-Build Done Right
DBIA Best Practices
https://dbia.org/best-practices/
Position Statements
Manual of Practice

## Slide 4
Design-Build Procurements

## Slide 5: Design-Build Procurements
Qualifications Based Selection
Best Value Selection
  Combination of price and technical
    Can also include schedule
  Weighted criteria
  Fixed Price Competitive Design
  Build-to-Budget
  Integrated Assessment and Trade-off
Low Bid

## Slide 6
PROCUREMENT INCENTIVES

## Slide 7: Stipends
A stipend is an amount paid by the owner to those shortlisted responsive proposers who are unsuccessful in obtaining contract award.
Encourages participation and innovation
DBIA endorses the use of stipends
Federal sector, including FHWA, encourages the use of stipends
Various industry surveys have shown stipends ranging from 0.01% to 0.25% of the project budget
Check jurisdictional limitations

## Slide 8: A+B Bidding
Under “A + B” or cost-plus-time bidding, two factors are considered in low bid determination:
  “A” component is the traditional price bid
  “B” component is calendar days to completion
  Formula: A + (B x Daily Cost) = Bid value
    Daily Cost is determined by the Owner and provided to the Proposers in the RFP documents

## Slide 9: Other Procurement Incentives
Alternative Technical Concepts
Local Preference
ROW credits

## Slide 10
Contract Incentives and Disincentives

## Slide 11: Time-Based Incentives
Can be used throughout the project term
Contract must be clear as to what constitutes “completion” for a bonus
Contract must address how delays, time extensions and contract terms affect the incentives

## Slide 12: Time-Based Incentives
Consider the reasoning behind using them
  Does the Owner benefit from early completion?
  Does the bonus really incentivize the Design-Builder?
  Can the Design-Builder game the bonus scheme?

## Slide 13: Completion Bonuses
Daily or fixed amount bonuses for early completion
  Daily amount
    Set by the Owner
    Based on the daily cost saved
    Note Design-Builder benefits regardless by saving on daily overhead
  Fixed amount
    Design-Builder may not proceed apace if the date will not be met

## Slide 14: Completion Bonuses for Revenue Projects
Daily or Fixed Amount
Tied to revenue service
Options include:
  Daily amount based on daily cost saved and expected revenues
  Fixed Amount, including fixed amount for timely completion
  A portion of the revenue earned by the Owner during the period between early completion and planned completion
Need to be coordinated with other aspects of the work, such as toll services and financing

## Slide 15: The Disincentive: Liquidated Damages
Damages agreed upon prior to contract execution
Legal sufficiency
  Actual damages must be difficult to ascertain
  Must be a reasonable measure of damages in light of circumstances at the time of contracting
  Cannot be a penalty
Considerations
  Sole remedy against design-builder for specified costs
  Can be combined with actual damages for other costs
  Should be commercially reasonable
  Need a clear trigger for the assessment of LDs
  Ceilings on the total amount of LDs
  Will the Design-Builder just price them?

## Slide 16: Liquidated Damages for Delay
Step-down between Substantial Completion and Final Acceptance
Can be used throughout the project term
Public agencies have wide berth in setting the amounts
Liquidated damages versus stipulated damages

## Slide 17: Other Incentives
Award Fee program
  Bonus incentives for meeting pre-determined performance criteria for performance guarantees, quality, claims management, timely delivery of submittals, site safety or other areas
Risk sharing
Allowances with risk sharing
Contingency pool
  Contingency amount established by owner or negotiated
  Change orders for eligible events are paid out of contingency
  Remaining contingency shared by contractor and owner
  Risk of insufficient contingency can be a project risk or assigned to a party
Long term warranties
O&M responsibility

## Slide 18: Other Disincentives
Withholding portions of monthly payments
Liquidated damages for performance
  Buy-downs of performance guarantees to a specific level
  Substitutions of key personnel
  Environmental non-compliance
  “Lane rentals”
  Deductions for noncompliance (more typical in P3s)
Disincentives are enforceable only if they meet liquidated damage prerequisites

## Slide 19: QUESTIONS?
Evan Caplicki
NOSSAMAN LLP
777 South Figueroa Street, 34th Floor
Los Angeles, California 90017
T 213.612.7877
M 512.809.5629
ecaplicki@nossaman.com