## Slide 1: Design-Build Process Utilizing Negotiated Selection
Notes: Negotiation = The act or process designed to produce an agreement

## Slide 2: Design-Build Process Utilizing Negotiated Selection
Discussion Topics
DBIA Best Practices
Manual of Practice
Overview of Negotiated Selection
Private vs Public
Negotiated Selection Process
Contract Terms/Issues

## Slide 3: Design-Build Process Utilizing Negotiated Selection
DBIA Best Practices
Design-Build Done Right
DBIA Best Practices
  https://dbia.org/best-practices
Position Statements
Manual of Practice
  D-B Process using Negotiated Selection

## Slide 4: Design-Build Process Utilizing Negotiated Selection
MOP - Overview of Negotiated Selection
Strategic Planning
  Business Need for Project
  Project Definition
  Choice of Project Delivery Method
Selection of Design-Builder
  Short Listed Teams
  Interview/Evaluation
  D-B Selected

## Slide 5: Design-Build Process Utilizing Negotiated Selection
Overview of Negotiated Selection – cont.
Project Definition (Pre-Construction)
  Programming & Preliminary Design
  Estimating Scheduling
Design-Build Contract Award
  Design not yet Completed
  GMP Established

## Slide 6: Design-Build Process Utilizing Negotiated Selection
Private vs Public
Private Sector
    Shortlisted Teams (experience)
    Proposals Include:
      The contractors team
      Schedule
      Fees/GC’s
    Selection – Team/Price
    Contract is Negotiated using Industry Standard or Owner’s template.
Notes: Discuss Regent experience (reference Bear River Middle School)
Selection Process
Use of DBIA contract form

## Slide 7: Design-Build Process Utilizing Negotiated Selection
Private vs Public
Public Sector
Can the Public Sector Engage in Negotiated Design-Build?
  Pre-Qualification is Defined Process (state statutes)
  Price is Part of the Selection Process (most statutes)
  Some Statutes (PCC 10191 & PCC 22164) Permit limited Negotiations
  Charter Cities or other local agencies may have more Flexibility
    San Francisco Airport Authority

## Slide 8: Design-Build Process Utilizing Negotiated Selection
Private vs Public
PCC 10191(d)(4)
  “Where a best value selection method is used, the department may reserve the right to request proposal revisions and hold discussions and negotiations with responsive proposers, in which case the department shall so specify in the request for proposals and shall publish separately or incorporate into the request for proposals applicable procedures to be observed by the department to ensure that any discussions or negotiations are conducted in good faith.”

## Slide 9: Design-Build Process Utilizing Negotiated Selection
Private vs Public
Public Sector – Limited Negotiations cont.
  RFP Stage
    Confidential Meetings
      Purpose
      Scope of Meeting(s)
      What can be discussed?
  Post Award
    Scope Confirmation
    Contract Language
Consult your legal Council!
Notes: Confidential Meetings
How Many?
What can be discussed?
Who should attend?
How to respond?
Confidential information?
Need to Clarify Information?

## Slide 10: Design-Build Process Utilizing Negotiated Selection
Public Sector
Judicial Council of California(GC 70391-70394)
  Two-Step Process
  Prequalification Phase
  Shortlisted Teams
    Proposal Interview
    Fees/GC’s
    Best Value Determination (Price must be considered)
    Contract Negotiated using Owner’s template.

## Slide 11: Design-Build Process Utilizing Negotiated Selection
Public Examples
    San Francisco Airport Authority
      Selection Based Primarily on Qualifications
        Team Qualifications
        Key Personnel
        Previous/Similar Project Experience
        Design Management Experience
        Project Management Experience
      Price is Optional
          Programming Services (Lump Sum)
          Design Builder Management Cost (Lump Sum)
          Bond Fee (Lump sum)
          Overhead and Profit Fee (Lump Sum)

## Slide 12: Design-Build Process Utilizing Negotiated Selection
Public Examples con’t
    San Francisco & Oakland State Building Projects
      State’s first Design Build Project’s
      “Design-Build Concept” Authorized
      Emphasized Design due to Location of Projects
      Shortlist Based Primarily on Qualifications
        Team Qualifications
        Key Personnel
        Previous/Similar Project Experience
        Prominence of Architects
      Selection based on Design Competition
        Price Negotiated
        Contract Negotiated
Notes: 1994 thru 1998
No state design build statute at the time.
We created the process as we went!

## Slide 13: Design-Build Process Utilizing Negotiated Selection
Contract Terms
May not need a Stipend
Savings Clause – Can you have them?
Performance Incentives
  Share Project Cost Savings
  Pay Early Completion Bonus
  May not be permissible in Public Contracts
Pre Guaranteed Maximum Price Phase
Guaranteed Maximum Price Phase

## Slide 14: Design-Build Process Utilizing Negotiated Selection
Questions